## Sheet1
Work Estimation Details |  | Optimistic | Most Likely | Pessimistic | Confidence | 75% | 85% | 95% | 99.5% | Supporting Document Links: (Enter Links to Requirements, Specifications, or other supporting documents in this column)
SDLC Phases | Activity/Task (Requirement number) | Effort Hrs | Effort Hrs | Effort Hrs | Factor | Confidence | Confidence | Confidence | Confidence
TensorFlow Design
AI Outline | REQ 1 | 2 | 3 | 7 | 0.83333 | 3.5 | 4.3333 | 5.1667 | 6
Software Prototype | REQ 2 | 6 | 8 | 11 | 0.83333 | 8.1667 | 9 | 9.8333 | 10.6667
Blender |  |  |  |  | 0 | 0 | 0 | 0 | 0
Design 3d Model | REQ 3 | 5 | 7 | 9 | 0.66667 | 7 | 7.6667 | 8.3333 | 9
Compatibilty with TensorFlow | REQ 4 | 1 | 2 | 5 | 0.66667 | 2.3333 | 3 | 3.6667 | 4.3333
Software Integration & Testing |  |  |  |  | 0 | 0 | 0 | 0 | 0
Build test cases | REQ 5 | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2.6667 | 3
Integrate real-world sensors | REQ 6 | 3 | 5 | 7 | 0.66667 | 5 | 5.6667 | 6.3333 | 7
Robotic Legs Integration |  |  |  |  | 0 | 0 | 0 | 0 | 0
Design & build physical model | REQ 7 | 1 | 2 | 3 | 0.33333 | 2 | 2.3333 | 2.6667 | 3
Hardware testing & integration |  |  |  |  | 0 | 0 | 0 | 0 | 0
Implement test cases in physical world | REQ 8 | 4 | 6 | 9 | 0.83333 | 6.1667 | 7 | 7.8333 | 8.6667
Optimize Code | REQ 9 | 2 | 3 | 4 | 0.33333 | 3 | 3.3333 | 3.6667 | 4
Debugging | REQ 10 | 5 | 7 | 9 | 0.66667 | 7 | 7.6667 | 8.3333 | 9
[5 empty] | 0 | 0 | 0 | 0 | 0
Work Estimate Totals |  | 30 | 45 | 67 |  | 46.1667 | 52.3333 | 58.5 | 64.6667